## Instructions
Canadian Condominium Reserve Fund Study Template
User Guide
1. Purpose: this workbook estimates reserve fund requirements, forecasts major
capital expenditures, and assesses annual owner contributions. All figures are
estimates only and actual costs and timing will vary.
2. Yellow cells are user inputs; navy/white cells contain formulas. Do not overtype
formula cells.
3. Update component condition, remaining life, replacement cost, inflation, and the
current reserve balance annually.
4. GST/HST treatment must be confirmed with the condominium corporation's accountant
and the applicable provincial rules before finalising any budget.
5. Study assumptions should be reviewed by a qualified reserve fund professional and
aligned with applicable provincial condominium legislation.
6. Worksheets are not protected; edit freely and keep a backup copy.
Property Profile
Condominium corporation | Maple Heights Condominium Corporation No. 184
City | Toronto
Province | Ontario
Study date | 2026-04-15
Fiscal year end | 2026-12-31
Reserve fund balance | 485000
Annual inflation assumption | 3%
Recommended contingency | 5%
GST/HST assumption | 13%
Prepared by | Sophie Tremblay, Reserve Planning Consultant

## Components
Component ID | Building Element | Category | Location / City | Last Renewal Date | Current Condition | Remaining Life (Years) | Useful Life (Years) | Current Replacement Cost (CAD) | Annual Inflation (%) | GST/HST Included? | Responsible Contact | Priority | Notes | Projected Renewal Year | Inflated Replacement Cost (CAD)
RC-001 | Roof membrane | Building envelope | Toronto | 2016-06-15 | Fair | 5 | 25 | 185000 | 3% | No | Liam Chen | High | Full replacement incl. insulation
RC-002 | Balcony repairs | Building envelope | Toronto | 2019-08-20 | Good | 8 | 30 | 240000 | 3% | No | Emma Wilson | Medium | Concrete restoration and railings
RC-003 | Domestic water boilers | Mechanical | Toronto | 2018-03-10 | Fair | 4 | 20 | 92000 | 3% | Yes | Noah Martin | High | Two boilers, quote pending
RC-004 | Garage membrane | Parking | Toronto | 2014-05-01 | Poor | 2 | 15 | 310000 | 3% | No | Olivia Roy | Critical | Active leaks reported P2 level
RC-005 | Elevators | Vertical transportation | Toronto | 2021-09-12 | Good | 12 | 25 | 425000 | 3% | Yes | Lucas Brown | Medium | Modernisation of both cabs
RC-006 | Domestic water piping | Plumbing | Toronto | 2008-07-15 | Fair | 7 | 40 | 275000 | 3% | No | Sophie Tremblay | High | Copper risers showing corrosion
RC-007 | Corridor flooring | Interior finishes | Toronto | 2020-01-25 | Good | 9 | 12 | 78000 | 3% | Yes | Ethan Singh | Low | Carpet tile replacement
RC-008 | Fire alarm system | Life safety | Toronto | 2017-11-30 | Fair | 6 | 20 | 135000 | 3% | No | Charlotte Nguyen | High | Panel and device upgrade
RC-009 | Domestic hot-water tanks | Mechanical | Toronto | 2022-04-18 | Good | 10 | 15 | 68000 | 3% | Yes | William MacDonald | Medium | Storage tanks, 3 units
Total current replacement cost

## Projection
Year | Opening Reserve Balance | Planned Contributions | Contribution Increase (%) | Investment Income | Component Capital Expenditures | Contingency Reserve | Ending Reserve Balance | Required Annual Contribution | Minimum Balance Alert | Contribution per Unit (Annual)
2026 |  | 155000 | 3%
2027 |  |  | 3%
2028 |  |  | 3%
2029 |  |  | 3%
2030 |  |  | 3%
2031 |  |  | 3%
2032 |  |  | 3%
2033 |  |  | 3%
2034 |  |  | 3%
2035 |  |  | 3%
2036 |  |  | 3%
2037 |  |  | 3%
2038 |  |  | 3%
2039 |  |  | 3%
2040 |  |  | 3%
2041 |  |  | 3%
2042 |  |  | 3%
2043 |  |  | 3%
2044 |  |  | 3%
2045 |  |  | 3%
Component Lookup
Select Component ID | RC-004
Component Timing Table
Component ID | Building Element | Projected Renewal Year | Inflated Replacement Cost (CAD)

## Dashboard
Reserve Fund Study — Executive Summary
Key Metric | Value | Category | Current Replacement Cost
Current reserve fund balance |  | Building envelope
Total projected capital expenditures (2026-2045) |  | Mechanical
Average annual capital expenditure |  | Parking
Recommended annual reserve contribution (2026) |  | Vertical transportation
Recommended monthly contribution per unit |  | Plumbing
Components rated Poor or Critical |  | Interior finishes
Years with a projected deficit |  | Life safety
Funding status
Peak expenditure year
Selected component (lookup)
Inflation assumption (% of cost growth)